## FB BYB
Boost Your Business With Facebook + IGHub Training Delivery Checklist
Name of Project/ Program:
S/N | Project ACTIONS to FOLLOW-Up with relevant Groups & ensure promptly done | Category | Responsibility | NOTES & Remarks (with Periodic Updates, learnings, observations & comments)
PRE-SESSION
0 | Program Campaign & Training Publicity(City, State, Nationwide via active Online & Offline Cha | PRE-SESSION
1 | Letter Of Introduction | PRE-SESSION
2 | Schedule Training On Portal | PRE-SESSION
3 | Participant Pre-Registration + Pre-Qualification (L1 or L2) | PRE-SESSION
4 | Design & Send Creatives For Trainer | PRE-SESSION
5 | Call & SMS Partcipants To Confirm Availability | PRE-SESSION
6 | Trigger Request for Refreshments | PRE-SESSION
7 | Notify Trainer of Confirmed Participants | PRE-SESSION
8 | Notify Food/ Refreshments Vendor | PRE-SESSION
9 | Send All Links & Trainer ToolKit To Trainers Within 24hrs | PRE-SESSION
10 | Pick Up Training Props & Venue Branding Materials | PRE-SESSION
11 | Ensure Contents Slides Updated[IGHub + FB L1 or L2 + Post Session Information e.g Feedback Link, FB BYB Group , FB Blueprint for Continous Learning] | PRE-SESSION
12 | Ensure that Official Fonts Are Installed & Working Properly On Training Device [Laptop, Desktop etc]
MID-SESSION
13 | Eearly Arrival At Training Venue | MID-SESSION
14 | Set up & Test All Training Aids At Venue [ Projector Or TV display, Cables, Extension, Power Plugs, Sound Check for Audio & Video Etc] | MID-SESSION
14 | Ensure Proper Venue Branding With Props | MID-SESSION
15 | Execute & Deliver Training Within Appropriate Duration (4-6hrs) | MID-SESSION
16 | Ensure During Session Photo Coverage (Trainer, Activity Period, Break Period etc) | MID-SESSION
17 | Online Posts, Tags & Mentions On Social Platforms During Session Activities | MID-SESSION |  | Ensure Participants to Share Activities Online (Facebook, Instagram, Twitter, LinkedIN) using official hashtags during break period
18 | Display Participant Further Information Slide [IGHubFeedback Link, FB BYB SMB Group Url, Fb Blueprint Url customised for Nigerian SMBs] | MID-SESSION |  | Administer Feedback Link Immediately Session Ends At Training Venue Before Participants Leave
19 | Ensure All Participants Are Signed Up Properly (Attendance confirmation) | MID-SESSION
20 | Answer All Questions Professionally & Note the ones to be escalated to IGHub with contact details of participants | MID-SESSION
21 | Take End Of Session Parctipant Group Photos With Branding Props | MID-SESSION
22 | End Session Officially & Appreciate Host Organisation | MID-SESSION
23 | Take & Record Live Feedback + Testimonials & Encourage Participants to Share Online With Official Hashtags [#boostyourbusinessng & #IGHubAfrica] | PRE-EVENT
23 | POST-SESSION | POST-SESSION
24 | Remember 10 Rules of Training Engagement (Check /Scan throuDocument | POST-SESSION
25 | Ensure Engagement & Participant Action Learning | POST-SESSION
26 | Capture & Record Immediate Actions Taken + Potential Success Stories [e.g FB & IG Business Pages Opened + Confirm use of Whatsapp Business] | POST-SESSION
27 | Encourage Online Posts, Tags & Mentions On Social Platforms After Ending Training Activities | POST-SESSION
29 | Follow-Up on Feedback Form Completion for E-Certificate (Email, SMS, Whatsapp Group, FB BYB Trainer Network Group, FB BYB SMB Group ] | POST-SESSION
30 | Follow-UP on Onboarding to FB BYB SMB Group/Community (Email, SMS, Whatsapp Group,] | POST-SESSION
31 | Follow-Up on FB Blueprint (Offical Customised Link for Nigerian SMBs) (Email, SMS, Whatsapp Group, FB BYB SMB Group ] | POST-SESSION
POST-SESSION
REPORTS
35
36 | Submit Official Training Report via link in fbportal.ighub.com.ng [ 12 Hrs SLA]
37 | *Send Engagement / Participants Action Details via fbportal.ighub.com.ng [Count Of FB & Or IG Pages Created, AD activity Campaign/ Test [E.g L2 Session], FB Page Manager Download etc]
38 | Send Training Session Photos (Minimum of 10 Good & Acceptable Quality) via mail to fbtrainers@ighub.com.ng
39 | Send Complete & Accurate Participants Attendance List (Excel Format) via mail to fbtrainers@ighub.com.ng
40 | Prepare & Submit Training Invoice with Appropriate Details [After all above reports have been complied with accurately)
41
NOTES, REMARKS, HIGHLIGHTS & SUMMARY
1
2
3
4
5
6
7
8
9
10
11
FB BYB 2018

## PRM
DBF Progress Tracker Checklist for DBA M1-S11 ProjecTeam
Name of Project/ Program: |  |  |  | ProjecTeamLEAD | Debola Ogundimu |  |  | Duration/ Date(s): | 4-Saturdays (June 03, 10, 17, & 24, 2017)
S/N | Project ACTIONS to FOLLOW-Up with relevant Groups & ensure promptly done | Category | Relevant DBF Groups-in-Charge | Action Follow-Up Team | Responsibility Teamate | Start Date | End Date | Status (Done/ On-going/ Pending) | NOTES & Remarks (with Periodic Updates, learnings, observations & comments)
1 | Implement Orientation & Equipping (O&E) session for ProjecTeamembers (c/o an AVC) | PRE-EVENT | Strategy & Programs | AVC/VC | Debola | March 7 2017 | March 14 2017 | DONE
2 | Produce Concept Note | PRE-EVENT | Strategy & Programs | Design & Reporting | Ayo | 2017-05-01 | 2017-05-20 | DONE
3 | Design/Update Program Slides | PRE-EVENT | Strategy & Programs | Design & Reporting | Ayo | 2017-05-01 | 2017-05-24 | 80% COMPLETE | Mr Kayode slide
4 | Update About DBF slide | PRE-EVENT | Strategy & Programs | Design & Reporting | Ayo | 2017-05-02 | 2017-05-25 | DONE
5 | Design/Update Facilitator's slide & profile | PRE-EVENT | Strategy & Programs | Design & Reporting | Ayo | 2017-05-02 | 2017-05-24 | ONGOING
6 | Prepare Video testimonial clips | PRE-EVENT | Strategy & Programs | Design & Reporting | Ayo | 2017-05-03 | 2017-05-27 | ONGOING | segun
7 | Prepare Video clips loaded on laptop | PRE-EVENT | Strategy & Programs | Design & Reporting | Ayo | 2017-05-03 | 2017-05-28 | ONGOING
8 | Produce invite to be sent to alumni database (SMS & Emails) | PRE-EVENT | Strategy & Programs | Design & Reporting | Ayo | 2017-06-03 | 2017-06-24 | Pending
9 | Update Welcome Address | PRE-EVENT | Strategy & Programs | Design & Reporting | Ayo | 2017-05-15 | 2017-05-24 | DONE | send out 19th june
10 | Produce Program Agenda | PRE-EVENT | Strategy & Programs | Design & Reporting | Ayo | 2017-05-22 | 2017-05-27 | ONGOING | sent 4 approval june1st
11 | Send invites to speakers & confirm availability | PRE-EVENT | Communication & Database | Mobilization | Dimson | 2017-06-27 | 2017-07-03 | ONGOING
12 | Send invite to alumni database (SMS & Emails) | PRE-EVENT | Communication & Database | Mobilization | Dimson | 2017-05-08 | 2017-05-23 | ONGOING | This will be sent a minimum of 3 times - once every week
13 | Send invite to registered trainee of pervious set who didn't attend (Emails) | PRE-EVENT | Communication & Database | Mobilization | Dimson | 2017-05-08 | 2017-05-23 | DONE
14 | Follow-Up With Faculty | PRE-EVENT | Communication & Database | Mobilization | Dimson | 2017-05-08 | 2017-05-23 | ONGOING
15 | Send notification to shortlisted applicants | PRE-EVENT | Communication & Database | Mobilization | Dimson | 2017-05-29 | 2017-05-31 | DONE | minimum of one email sent every week
16 | Send notification to non-shortlisted applicants | PRE-EVENT | Communication & Database | Mobilization | Dimson | 2017-05-29 | 2017-05-31 | Pending | minimum of one email sent every week
17 | Produce Registration Forms | PRE-EVENT | Communication & Database | Resourcing & Materials | Yetunde | 2017-06-01 | 2017-06-24 | Pending
18 | Produce Name Tags for Attendees | PRE-EVENT | Communication & Database | Resourcing & Materials | Yetunde | 2017-06-01 | 2017-06-24 | Pending
19 | Send Pre & Post-Session e-notes | PRE-EVENT/DURING EVENT | Communication & Database | Mobilization | Dimson | 2017-06-01 | 2017-06-24 | Pending | Will be sent at least one week before each class
20 | Social Media Publicity Coordination | PRE-EVENT | Media & Publicity | Mobilization | Dimson | 2017-05-01 | 2017-05-31 | ONGOING
21 | Send IV to Daystar Media & Sounds | PRE-EVENT | Media & Publicity | Mobilization | Dimson | 2017-05-15 | 2017-05-23 | ONGOING
22 | Design and print Banner | PRE-EVENT | Media & Publicity | Mobilization | Dimson | 2017-05-01 | 2017-05-24 | DONE
23 | Ad Contact Details Selection (Email/Phone) | PRE-EVENT | Media & Publicity | Mobilization | Dimson | 2017-05-01 | 2017-05-05 | DONE
24 | Ad Materials Submission to Church | PRE-EVENT | Media & Publicity | Mobilization | Dimson | 2017-05-08 | 2017-05-22 | DONE
25 | Ad on Church’s Website | PRE-EVENT | Media & Publicity | Mobilization | Dimson | 2017-05-08 | 2017-05-24 | DONE
26 | Creation of Online Portal for Registration | PRE-EVENT | Media & Publicity | Mobilization | Dimson | 2017-05-01 | 2017-05-05 | DONE
27 | Ad on Church (Banner/Bulletin) | PRE-EVENT | Media & Publicity | Mobilization | Dimson | 2017-05-10 | 2017-05-28 | DONE
28 | Periodic Update of Online Applications to Volunteers | PRE-EVENT | Media & Publicity | Mobilization | Dimson | 2017-05-08 | 2017-05-31 | ONGOING
29 | Get Budget Approval | PRE-EVENT | Admin & Finance | Resourcing & Materials | Yetunde | 2017-05-01 | 2017-05-05 | ONGOING
30 | Collect Budget Fund/Items From Church | PRE-EVENT | Admin & Finance | Resourcing & Materials | Yetunde | 2017-05-26 | 2017-05-31 | Pending
31 | Ensure Equipment in good condition prior to program | PRE-EVENT | Admin & Finance | Resourcing & Materials | Yetunde | 2017-05-27 | 2017-06-24 | DONE
32 | Apply For Venue | PRE-EVENT | Operations & Logistics | Resourcing & Materials | Yetunde | 2017-05-01 | 2017-05-05 | DONE
33 | Make Requisition for Equipment and Materials e.g (laptops) | PRE-EVENT | Operations & Logistics | Resourcing & Materials | Yetunde | 2017-05-22 | 2017-05-31 | Pending
34 | Get Approval for Attendees Car Park | PRE-EVENT | Operations & Logistics | Resourcing & Materials | Yetunde | 2017-06-02 | 2017-06-24 | Pending
35 | Prepare Post-Session e-notes | DURING EVENT | Strategy & Programs | Design & Reporting | Ayo | 2017-06-03 | 2017-06-24 | Pending
36 | Produce Post-Session Report | DURING EVENT | Strategy & Programs | Design & Reporting | Ayo | 2017-06-03 | 2017-06-24 | Pending
37 | Assign Volunteers on Registration Desk | DURING EVENT | Communication & Database | Resourcing & Materials | Yetunde | 2017-06-02 | 2017-06-24 | Pending
38 | Participants' Head Count (Twice) | DURING EVENT | Communication & Database | Resourcing & Materials | Yetunde | 2017-06-03 | 2017-06-24 | Pending
39 | Collect & Collation Feedback Forms | DURING EVENT | Communication & Database | Resourcing & Materials | Yetunde | 2017-06-03 | 2017-06-24 | Pending
40 | Collect Facilitators' Hampers & Cheque | DURING EVENT | Admin & Finance | Resourcing & Materials | Yetunde | 2017-06-02 | 2017-06-24 | Pending
41 | Venue Arrangement and Set-Up for 2000 particpants | DURING EVENT | Operations & Logistics | Resourcing & Materials | Yetunde | 2017-06-02 | 2017-06-24 | Pending
42 | Ensure Squeeky Clean Rest Rooms (Male & Female) | DURING EVENT | Operations & Logistics | Resourcing & Materials | Yetunde | 2017-06-02 | 2017-06-24 | Pending
43 | Ensure hall is well-lit & Air-Conditioned | DURING EVENT | Operations & Logistics | Resourcing & Materials | Yetunde | 2017-06-01 | 2017-06-24 | Pending
44 | Set-up Registration Points | DURING EVENT | Operations & Logistics | Resourcing & Materials | Yetunde | 2017-06-02 | 2017-06-24 | Pending
45 | Ensure Paper Bins within the hall | DURING EVENT | Operations & Logistics | Resourcing & Materials | Yetunde | 2017-06-02 | 2017-06-24 | Pending
46 | Assign Protocols & Ushers | DURING EVENT | Operations & Logistics | Resourcing & Materials | Yetunde | 2017-06-02 | 2017-06-24 | Pending
47 | Purchase Refreshments for Facilitators & Volunteers | DURING EVENT | Internal Activities | Resourcing & Materials | Yetunde | 2017-06-02 | 2017-06-24 | Pending
48 | Volunteers Time-Log & Head Count | DURING EVENT | Internal Activities | Resourcing & Materials | Yetunde | 2017-06-03 | 2017-06-24 | Pending
49 | Facilitators & CoreTeam Welfare | DURING EVENT | Internal Activities | Resourcing & Materials | Yetunde | 2017-06-03 | 2017-06-24 | Pending
50 | Volunteers Welfare | DURING EVENT | Internal Activities | Resourcing & Materials | Yetunde | 2017-06-03 | 2017-06-24 | Pending
51 | Produce Post-Program Report | POST-EVENT | Strategy & Programs | Design & Reporting | Ayo | 2017-06-24 | 2017-06-30 | Pending
51 | Feedback Forms Analysis | POST-EVENT | Communication & Database | Design & Reporting | Ayo | 2017-06-03 | 2017-07-24 | Pending
53 | Provide Post-Program Advisory and Supports | POST-EVENT | Supports & Evaluation | Design & Reporting | Ayo | 2017-06-24 | 2017-07-24 | Pending
54 | Create a framework for the 3-levels of milestone post-event interventions | POST-EVENT | Supports & Evaluation | Design & Reporting | Ayo | 2017-06-03 | 2017-06-24 | Pending
55 | ProjecTeam PERFORMANCE RATING @1st TPM after the program ends | POST-EVENT | DBF | AVC/VC | M1-S10 TEAM | 2017-07-01 | 2017-07-04 | Pending
NOTES & REMARKS
1 | The major function of ProjecTeamembers on any DBF project is to FOLLOW-UP on the respective DBF Groups and Teams under them. They do not do the job. They only *follow-up on those doing it
2 | Each ProjecTeam shall be composed of only 3-ProjecTeamembers and the ProjecTeamLEAD, making a total of 4-personnel
3 | The key FOLLOW-UP roles of the ProjecTeamembers cover three categories:- (1) Design & Reporting, (2) Mobilization, (3) Resourcing & Materials
4 | An algorighm for selecting ProjecTeams shall be:- <1>Last ProjecTeamLEAD of the new program/ event; <2>ProjecTeamLEAD for next 2 projects on DBF callendar and <3>any randomly-selected Volunteer of choice by ProjecTeamLEAD
5 | There must be at least a lady on every ProjecTeam
6 | The randomly-selected Volunteer by the ProjecTeamLEAD must not be same person chosen by the last two concluded projects
7 | The first thing every ProjecTeam must do is arrange a Team Orientation & Equipping (O&E) for the ProjecTeamembers to be facilitated by an AVC (on rotation) and supported by Peter
8 | The O&E training should cover areas like: Relationship-Building & Management, Expectation Clarification, KPI awareness and measures, Project Attitude & Behaviors, Communication, Reporting & Feedback Standards, etc.
9 | At the end of each Project or Program, the ProjecTeam must ensure 3-levels of post-session interventions
>> first post-event eNOTE to thank them for coming and share agreed synopsis of the sessions not later than 1-week after the event
>> second post-event eNOTE to share useful related links and information for further learning
>> Cluster Grouping or PMG activation with installed Leaders at each Cluster or PMG for further interraction
>> Any other resource or activity of benefits related to the participants of the just-concluded program/ event
10 | At the first TPM after each program ends, all Volunteers shall rate the performance of every ProjecTeam as a team and the individuals along certain pre-agreed variables or points
11 | The ProjecTeam Performance rating shall be structured for learning, improvement and advancement purposes and never to tear down or criticize people
DBA Module-1, Set-11 (M1-S11)